LOOGOOTEE MFG. — TRAINING SIMULATION G1 — Gate Entry Document Controller Commissioning and UNS Integration Status: IN PROGRESS ¦ Reference: Rack Phased Development Plan Rev 1.2

Phase Overview

Gate G1 confirms that all 11 controllers are commissioned, all simulation programs are running, and all data is verified publishing correctly to the Unified Namespace. The OT data layer must be complete and verified before the IIoT stack is built on top of it. No Phase 2 infrastructure work begins until this gate is passed.

Full phase detail — purpose, key activities, demonstration value, and implementation notes — is documented in the Rack Phased Development Plan Rev 1.2, located in 06_rack_documentation/rack_phased_development_plan/.

Gate Entry Criteria

All criteria must be satisfied and documented before this gate is passed and the next phase is authorized to begin. Check each item at time of gate review.

| # | Criteria | ✓ |
| --- | --- | --- |
| 1 | All 11 controllers physically mounted and powered in 42U rack | ☐ |
| 2 | Rack power infrastructure complete — both dedicated 20A circuits landed and verified | ☐ |
| 3 | All 11 controllers commissioned — programs downloaded and running | ☐ |
| 4 | Simulated production routines running on all platforms — fault cycling, cycle times, part counts active | ☐ |
| 5 | All controllers publishing ISA-95 named Sparkplug B metrics to Mosquitto broker | ☐ |
| 6 | Sparkplug B payload verified end to end — MQTT Explorer confirmation on all devices | ☐ |
| 7 | Tag naming validated against ISA-95 standard — Tier 1 and Tier 2 confirmed on all platforms | ☐ |
| 8 | All 13 protocol paths verified active — DF1, DH-485, Modbus RTU, EtherNet/IP, PROFINET, PROFIBUS, EtherCAT, OPC-UA, S7 PUT/GET, CIP Safety, MQTT, Sparkplug B, IO-Link broker path | ☐ |
| 9 | Pre-commissioning program backup complete — all 11 controllers at commissioned state | ☐ |
| 10 | All program files committed to version control at Gate G1 revision | ☐ |
| 11 | MicroLogix 1000 program spec updated to final revision | ☐ |
| 12 | Gate G1 sign-off documented in this record | ☐ |

Gate Sign-Off Record

Complete this section when all gate criteria have been satisfied. Gate sign-off authorizes commencement of the next phase.

| Gate | G1 |
| --- | --- |
| Phase Name | Controller Commissioning and UNS Integration |
| Date Passed |  |
| Signed Off By |  |
| All Criteria Satisfied | ☐ Yes ☐ No — conditions noted below |
| Conditions / Notes |  |
| Authorization to Proceed | ☐ Authorized ☐ Conditional ☐ Not Authorized |