LOOGOOTEE MFG. — TRAINING SIMULATION G7 — Gate Entry Document Independence Validation and Project Closeout Status: PLANNED ¦ Reference: Rack Phased Development Plan Rev 1.2

Phase Overview

Gate G7 is the final and most important gate. A colleague with no prior knowledge of the build performs the independence exercise using only the project documentation — no integrator assistance. The outcome confirms whether the documentation package is sufficient for independent operation and extension of the system. All identified gaps are resolved before the project is formally closed.

Full phase detail — purpose, key activities, demonstration value, and implementation notes — is documented in the Rack Phased Development Plan Rev 1.2, located in 06_rack_documentation/rack_phased_development_plan/.

Gate Entry Criteria

All criteria must be satisfied and documented before this gate is passed and the next phase is authorized to begin. Check each item at time of gate review.

| # | Criteria | ✓ |
| --- | --- | --- |
| 1 | Independence exercise colleague identified — technical background, no prior knowledge of Loogootee build | ☐ |
| 2 | Complete documentation package assembled and verified at current revision | ☐ |
| 3 | New equipment selected for independence exercise — physically present and ready for commissioning | ☐ |
| 4 | Colleague commissions new equipment and writes program using documentation only — no integrator assistance | ☐ |
| 5 | New equipment publishing to UNS — ISA-95 named Sparkplug B metrics verified in MQTT Explorer | ☐ |
| 6 | IO-Link sensor data flowing from new device — confirmed | ☐ |
| 7 | New equipment data appearing in Grafana dashboards automatically — no dashboard modifications needed | ☐ |
| 8 | Asset added to MaintainX by colleague independently — using documentation only | ☐ |
| 9 | Automated work order generated when threshold is breached — no integrator involvement | ☐ |
| 10 | Line supervisor visibility confirmed — colleague can see all data from the dashboard | ☐ |
| 11 | Independence exercise observation record complete — successes and gaps documented | ☐ |
| 12 | All identified documentation gaps resolved — documents updated before gate passage | ☐ |
| 13 | Lessons learned document complete | ☐ |
| 14 | All program files and configuration at final revision committed to version control | ☐ |
| 15 | Project archive index complete and committed to repository | ☐ |
| 16 | Gate G7 sign-off documented in this record — project formally closed | ☐ |

Gate Sign-Off Record

Complete this section when all gate criteria have been satisfied. Gate sign-off authorizes commencement of the next phase.

| Gate | G7 |
| --- | --- |
| Phase Name | Independence Validation and Project Closeout |
| Date Passed |  |
| Signed Off By |  |
| All Criteria Satisfied | ☐ Yes ☐ No — conditions noted below |
| Conditions / Notes |  |
| Authorization to Proceed | ☐ Authorized ☐ Conditional ☐ Not Authorized |